## Sheet1
Page | Pending Task | Blocker | Status | Time Estimation
Admin Page
| Total Active User, Total Blocked User, Total Active HODs | Dependent on AD/ID
| Total Department | It should be change or not with date filter as it if fixed.
| Application Usage Graph | Dependent on AD/ID
| User Management page | AD/ID
User Page | User Page: In Notification list there should be soft delete button. | Discussion Pending
File Manager Page | DWG file view inside modal | POC required
Need to clear this requirment | Dynamic Sub-Area addition | Discussion Pending
| User Page: Date filter in approved document list | Done

## Sheet2
Requirment | Days-Frontend | Days-BackEnd | Testing-Days | Total
1. Filter by doc type and doc size (in document list table). | 1 | 1 | 0.5 | 4 | Total Days = | 33.5
2. Need to show plant name in department card page. | 1 | 0 | 0.5 | 1.5
[Need to add a header (plant name in the department cards; need to add 440 with cpp2 and 1250 with cpp3].
3. Document type will increase + others will be present (librarian upload dropdown). | 2 | 2 | 1 | 5
4. Add an option for the user to upload a file; after uploading, the file will be received by the librarian, and the librarian will check and upload that file. | 3 | 3 | 1 | 7
5.Admin can show all types of documents. | 1 | 0 | 0 | 1
6. Restricted document request flow and list of restricted document in file manager page in new tab | 4 | 2 | 1 | 7
7. A restricted document request will go to the librarian. and to HOD also. | 4 | 3 | 1 | 8
8. For main head other than POWER O&M. The hierarchy will be like Power O&M, but with few changes in department name and number . of departments present in it. | Requirment not clear | Requirment not clear | Requirment not clear | 0
9. Search using keywords that are present in the file. | Yet to discuss and test search upon soft-copy is done | Yet to discuss and test search upon soft-copy is done | Yet to discuss and test search upon soft-copy is done
We need to upgrade the search; we can make the search content-wise.
(We can search by keywords that are in the files and need an advance search, like Amazon.)
10. User management will be handled by the librarian. | AD/ID dependency and will estimate after POC | AD/ID dependency and will estimate after POC | AD/ID dependency and will estimate after POC
11. User management page for admin for elevated access | AD/ID dependency and will estimate after POC | AD/ID dependency and will estimate after POC | AD/ID dependency and will estimate after POC